## Sheet1
Area | Control | Current_State | Gap_or_Risk | Priority (H/M/L) | Recommendation | Owner | Due_Date (dd-mm-yyyy)
Policies | Information Security Policy | Basic policy draft exists but not approved by management | Lack of formal approval and periodic review | H | Finalize, approve, and publish an Information Security Policy; set annual review cycle. | IT Manager | 2025-09-30
Access Control (IAM) | User Account Provisioning | Manual onboarding/offboarding of employees | Risk of orphan accounts and unauthorized access | H | Implement automated IAM with timely provisioning and deprovisioning processes. | IT Lead | 2025-10-15
Access Control (IAM) | MFA Enforcement | MFA enabled only for admin accounts | Regular user accounts lack MFA protection | M | Roll out MFA for all users accessing sensitive systems. | Security Team | 2025-10-30
Incident Response | IR Plan & Drills | Basic incident response plan exists but never tested | No assurance of team readiness in case of security incidents | H | Conduct tabletop IR exercises quarterly and update the plan based on lessons learned. | SOC Lead | 2025-11-30
Asset Management | Asset Inventory | Partial inventory maintained in spreadsheets | Risk of missing devices or shadow IT | M | Deploy automated asset discovery tools and maintain centralized inventory. | Ops Manager | 2025-10-31
Training & Awareness | Cybersecurity Training | Annual training conducted only for new hires | Existing staff lack updated awareness about phishing and ransomware | M | Implement quarterly phishing simulations and refresher training for all staff. | HR Head | 2025-11-15
Physical Security | Server Room Access | Server room has lock but no access logs | No way to track who enters critical areas | L | Install electronic access control with logging and regular audits. | Facilities | 2025-12-31